## Sheet2
Tentative Project Timelines for Greaves Cotton Ltd. AR 2025-26
Particulars | Responsibility |  | Tentative Date
| Greaves Cotton Ltd. | WyattPrism (WP)
Kick-off call with Greaves Cotton & WP | ü | ü | 04.03.26
Submission of the tentative project timelines & SOP sheet | - | ü | 04.03.26 & 05.03.26
Submission of the Questionnaire (For MD&A draft) | - | ü | 11.03.26
Submission of the Accounts & Stat Template | - | ü | 11.03.26
Approved theme received from client with Cover design suggestions | ü | - | 12.03.26
Submission of the cover design based on the approved theme | - | ü | 18.03.26
Receipt of the inputs from the verticals based on the Questionnaire shared | ü | ü | 18.03.26 to 23.03.26
Feedback & Finalization of the cover design | ü | ü | 25.03.26
First draft of the MD&A is shared | - | ü | 03.04.26
First round of non-stat content is shared (based on the approved theme) |  |  | 10.04.26
MD&A in design is shared (2 rounds of corrections addressed in the word file) | ü | ü | 14.04.26
Submission of the design pages of the Non-stats section (after addressing the 2 rounds of corrections in the word file) | ü | ü | 20.04.26
MD&A corrections in the design version and submit the updated version for the Board Meeting | ü | ü | 24.04.26
Receipt of the Stats and financials section (after Board Meeting) | ü | - | 08.05.26
Submission of revised MDA with all numbers updated | - | ü | 12.05.26
Submission of Secretarial and financial sections in a laid-out version | - | ü | 16.05.26
Continue designing of non-stat section | - | ü | 16.05.26
Feedback & submission of Secretarial and financial sections (3 rounds of changes) | ü | ü | 19.05.26
Submission of complete non-stats section in design | - | ü | 22.05.26
Design of the entire non-stat section and MDA is shared | - | ü
Feedback and near to the finalisation of the stats and financials section | ü | ü | 23.05.26
Revised design for non-stat section and MDA is shared | - | ü | 23.05.26
Proofreading of the non-stats section and MD&A is undertaken | - | ü | 27.05.26
Minor iterations are made and final file is shared for approval | ü | ü | 28.05.26
Cover to cover file of the Annual Report is shared (for uploading and emailing) | - | ü | 03.06.26
Artworking of the entire file is done and print-ready files are prepared | - | ü | 09.06.26
Tentative Greaves Cotton Ltd. AGM | End of July, 2026