## Sheet1
Tentative Project Timeline for Rainbow Children's Medicare Ltd. Integrated Annual Report 2024-25
Key Dates
Board Meeting | 1st week of May, 2025
Closure of the Report | 6th June, 2025
AGM | 30th June, 2025
Time Frame | Description | Responsibility
|  | Rainbow Children's Medicare Ltd. | WyattPrism (WP)
Week 1, 2 & 3
Jan 13 to Jan 31 | Submission of the tentative project timeline | - | ü
| Collection of repository - Image and content assets to be shared by the client with WP | - | ü
| Submission of Account & Statutory template | - | ü
| VC call with the Chairman Sir to take his input to draft the Chairman's Message & direction on the theme | ü | ü
| Submission of the Questionnaires for the Non-stats section | - | ü
Week 4, 5, 6 & 7
Feb 03 to Feb 28 | Feedback and approval on the template | ü | ü
| Submission of theme lines based on the our discussion | - | ü
| Feedback and finalization of theme for the report | ü | ü
| Submission of the Storyboard (flow of content for Non-stats) | - | ü
| Submission of the cover design based on the approved theme | ü | ü
| Feedback and approval on the Storyboard (for Non-stats section) | ü | ü
| Receipt of all inputs as per Storyboard (for Non-stats section) via questionnaire shared | ü | ü
| Submission of the revised cover based on the feedback | - | ü
| Feedback and finalization of the cover design | ü | ü
Week 8, 9, 10 & 11
Mar 03 to Mar 28 | First round of non-stat content is shared (based on the approved storyboard) | - | ü
| Submission of the draft MD&A | - | ü
| Feedback and revised non-stats content shared - 1st round | ü | ü
| Submission of a few non-stats pages in design | - | ü
| Feedback and share the non-stat content - 2nd round | ü | ü
| Feedback and shared the MD&A - 1st round | - | ü
Week 12, 13, 14, 15 & 16
Apr 01 to May 02 | Feedback received on the design pages of inside pages | ü | ü
| Submission of MD&A content for Board Meeting | - | ü
Board Meeting - Tentatively scheduled for 1st week of May, 2025
Week 17, 18, 19 & 20
May 05 to May 30 | Receipt of the Stats and financials section (after Board Meeting) | ü | -
| Continue designing of non-stat section | - | ü
| Submission of a few more design pages over and above previously shared | - | ü
| Submission of Secretarial and financial sections in a laid-out version | - | ü
| Submission of all the non-stats pages in design with updated information | - | ü
| Feedback and near to the finalisation of the stats and financials section (3/4 round of corrections) | ü | ü
| Finalisation of non-stat and MDA section | - | ü
Week 21
June 02 to June 06 | Proofreading of the non-stats section and MD&A is undertaken | - | ü
| Minor iterations are made and final file is shared for approval | ü | ü
| Cover to cover PDF of the Integrated Annual Report is shared for website and emailing | ü | ü
| Artworking of the entire file is done and print ready files are prepared and shared | - | ü
Rainbow Children's Medicare Ltd. AGM - 30th June, 2025
Please note:
Print file will be provided 3-4 working days post the release of web upload file
The deliverables mentioned in the timeline is subject to receipt of necessary information and inputs from the client at the right time