## Timelines
Tentative Timeline ¦ Triveni Engineering & Industries Limited AR 2025-26
Key Dates |  |  | Single Point of Contact
Closure | 2026-08-01 |  | IR team | Himanshu Sharma
Month | Process Description | TEIL | WP | By Date
2026-03-01 | Kick off call | P | P | 2026-03-23
| Submission of the Proposal and documents |  | P | 2026-03-30
2026-04-01 | Submission of Stat and financial templates |  | P | 2026-04-03
| Feedback on the Stat and financial templates | P |  | 2026-04-09
| Feedback and Finalize the Stat template | P | P | 2026-04-13
| Submission of Benchmarking Deck |  | P | 2026-04-21
| Call with Vice Chairman and Managing Director | P | P | 24-04-2026 to 29-04-2026
2026-05-26 | Submission of Proposed Themes |  | P | 2026-05-11
| Submission of 2nd round of Themes |  | P | 2026-05-15
| Submission of Proposed Storyboard | P |  | 2026-05-19
| Feedback and Finalisation of Themes | P | P | 2026-05-19
| Feedback and Finalisation of Storyboard | P | P | 2026-05-22
| Board Meeting (Tentatively) | P |  | 2026-05-27
| Submission of Cover Design |  | P | 2026-05-29
2026-06-01 | Feedback on the Cover Design | P |  | 2026-06-02
| Submission of 2nd round of Cover Design |  | P | 2026-06-05
| MDA draft comes from Client | P |  | 2026-06-08
| Feedback and Finalization of the cover | P | P | 2026-06-09
| Edit and Finalisation of MDA | P | P | 2026-06-15
| Received Financials (Standalone and Consolidated) from client | P |  | 2026-06-16
| Received BRSR, Directors Report and Annexures from Client | P |  | 2026-06-16
| Submission of 1st draft of narrative |  | P | 2026-06-17
| Submission of designed MDA |  | P | 2026-06-19
| Feedback on 1st draft of narrative | P |  | 2026-06-22
| Feedback on designed MDA | P |  | 2026-06-22
| Feedback and Finalisation of Narrative Draft | P | P | 2026-06-26
| Submission of layout BRSR,Directors Report and Annexures |  | P | 2026-06-25
| Submission of layout financials |  | P | 2026-06-26
| Finalization of MDA in design | P | P | 2026-06-29
2026-07-01 | Submission of 1st round of narrative pages in design |  | P | 2026-07-03
| Received 1st round of corrections in Statutory and Financial section | P |  | 2026-07-06
| Feedback on designed Narrative | P |  | 2026-07-08
| Submission of revised Statutory and Financial section |  | P | 2026-07-10
| Received 2nd round of corrections in Statutory and Financial section | P |  | 2026-07-14
| Feedback and Finalisation of Narrative in design | P | P | 2026-07-10
| Review and changes of the Statutory and Financial section | P | P | 15 July to 21 July 2026
| Review and changes of the Narrative and MD&A section | P | P | 11 July to 20 July 2026
| Near to the finalisation of all individual section | P | P | 21 July to 25 July 2026
| Cover to cover file of the Annual Report is shared |  | P | 2026-07-27
| Submission of Final corrections in cover to cover PDF |  | P | 2026-07-28
| Proofreading of narrative and MDA | P | P | 2026-07-29
| Final PDF shared for sign-off |  | P | 2026-07-30
| Web upload PDF shared |  | P | 2026-07-31
2026-08-01 | Print files shared |  | P | 2026-08-01

## Process
Non stat / Narrative | Timelines | MDA | Statutory | Financial | Timelines
Call with VCMD | April End - Early May | Draft to come after Q4 | Files come after Q4 Board Meeting |  | May End
Themes | Mid May | Draft to come after Q4 | Files come after Q4 Board Meeting |  | June & July
Storyboard | May End | WP to edit the Word file | Files typeset and shared
Cover Designs | May End | Edited file reviewed and closed | 2- 3 rounds of changes on PDF
Narrative Draft (Word file) | June- July | 2-3 rounds of changes on PDF
2-4 rounds of changes on PDF | July
Complete Book is shared and proofreading of Non Stat and MDA |  |  |  |  | July End - Aug Start
Report Signed off |  |  |  |  | 1st week of Aug